## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | As a user, I want to upload or select a contract so that I can start the compliance check. | M | - | The Developer | Done
2 | 2 | US-02 | As a user, I want to initiate the AI regulatory compliance check so that I can analyze my contract against selected regulations. | M | US-01, US-03 | The Developer | Done
1 | 1 | US-03 | As a user, I want to see a risk analysis and suggestions for my contract... | M | US-08 | The Developer | Done
2 | 2 | US-04 | As a user, I want the system to generate a rectified version of my contract in PDF format. | S | US-03 | The Developer | Done
2 | 2 | US-05 | As a user, I want to be able to download the Risk Analysis Suggestions and the Rectified Contract PDFs. | M | US-04 | The Developer | Done
2 | 2 | US-06 | As a user, I want an email notification containing the analysis and rectified contract to be sent to a specified recipient. | C | US-04, US-05 | The Developer | Done
1 | 1 | US-07 | As a user, I want a clear, interactive Streamlit front-end with a progress bar and status updates. | M | - | The Developer | Done
1 | 1 | US-08 | As an admin, I want to update and manage the regulatory documents in the system. | M | - | The Developer | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | US-07 | T-07.2 | Implement contract selection/upload component. | 2025-12-01 | 2025-12-02 | The Developer | Done | 4
1 | US-08 | T-08.2 | Create function to fetch and register external regulations. | 2025-12-02 | 2025-12-03 | The Developer | Done | 5
1 | US-03 | T-03.1 | Setup LangChain RAG pipeline with Groq. | 2025-12-01 | 2025-12-03 | The Developer | Done | 8
2 | US-02 | T-02.1 | Integrate RAG analysis pipeline into Streamlit UI. | 2025-12-15 | 2025-12-17 | The Developer | Done | 10
2 | US-04 | T-04.2 | Implement logic to extract and PDF-generate rectified contract. | 2025-12-16 | 2025-12-18 | The Developer | Done | 8
2 | US-06 | T-06.2 | Integrate mail sending into app.py (after successful analysis/rectification). | 2025-12-16 | 2025-12-18 | The Developer | Done | 8
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 |  |  | surya | Start having short, focused 'prompt reviews' before RAG integration. | Stop estimating tasks below 1 hour. | Continue daily stand-ups and breaking down user stories into small tasks. | Dedicated 1 hour after the stand-up on Day 5 for a RAG prompt review session.
2 | 2 |  |  | surya | Start preparing for the next dependency (e.g., deployment) earlier in the sprint. | Stop doing multi-day refactoring without a clear pause point. | Continue testing the full end-to-end flow daily. | Researched deployment options (Streamlit Cloud/Docker) on Day 7 of Sprint 2.
4
5
6
7